## OneApp
OneApp
S.No | Team | Issues | Person Responsible | Dependency | Date
1 | AWS | Architecture review and optimisation Explore, Advanced, Atlas, Traffic | ARB |  | 2017-12-01
|  | Presentation to board for approval | Sanjay |  | 2017-12-04
2 | Advanced Maps | Architecture revisit for Migration | Vishu | ARB | 2017-12-01
|  | Reverse Geocode - DB Clustering | Vishu | Ankesh | 2017-12-07
|  | Ingestion of Ver. 16.0 Map Data | Vishu | Sunil | 5th Jan
|  | Mireo Routing API @ Ver 16.0 | Piyush | Mireo | 25-Dec Tentative
|  | Batch processing and sharing of information to Data Team for Incremental Update - PoI (Edit a Place) | Balmukund |  | 2017-11-28
|  | Edit a Place - Migrate to Zoho | Anant |  | 2017-11-28
|  | Ingestion process of PoI Incremental Data - Batch | Vishu | Mamta | 2017-12-11
|  | Performance Testing & Deployment | Vishu | Aditya, Anant, Sonal | 2017-12-14
|  | Migration to AWS | Vishu |  | 2017-12-15
|  | Scheduler for UGC Patch Update to all repositories | Vishu | Data Team | 2017-12-11
3 | Explore | Architecture revisit for Migration | Vishu | ARB | 2017-12-01
|  | DB change to Couchbase Implementation, Caching and API Tuning | Vishu |  | 2017-12-12
|  | Http Mailer for SMS/ Email | Altamash | Tarini
|  | Migration to AWS | Vishu |  | 2017-12-14
4 | Marketing | Content rework for SMS | Tarini | Anant | 2017-12-06
|  | Content rework for Email | Tarini | Anant
5 | Vector | Generalised Layers for Zoom 4 | Mamta |  | 2017-12-10
|  | Vector Labelling Issues | Mamta | Parinita | 2017-12-15
|  | Zoom Level wise statistics | Mamta |  | 2017-11-29
|  | Reduction of Shield data on some Zoom Levels | Mamta | Ashutosh | 2017-12-15
|  | Railway Track - Metro/ Railway Seggregation and Color Coding for some specific cities | Mamta | Bhupesh | 2017-11-30
|  | Water Streams Center Line labelling issue for about 39 rivers | Mamta | Bhupesh | 2017-12-07
|  | Water Bodies and Green Area - Object selection at different zoom levels | Mamta | Bhupesh | 2017-11-30
|  | Label Normalization | Mamta, Mrs Verma
|  | Version 16.0 data handover | Mamta | Parinita
|  | Private routes suppression | Mamta |  | 2017-11-30
|  | Testing of PoI Incremental Data | Mamta
|  | Style Benchmarks | Abhinav |  | 2017-12-15
|  | Font Size Improvement Day, Night, Hybrid | Mamta | Mrs Verma, Abhinav, Pradeep, Rishin, Anant | 2017-12-15
|  | Tile Compilation (Advanced Lab Machines) | Mamta |  | 2017-12-30
|  | Feature Analysis | Priyanka, Pradeep | Mrs Verma
|  | Night Mode & Hybrid Style Sheet rework | Priyanka, Abhinav |  | 2017-12-22
|  | Raster/ Vector Combination RnD | Akram |  | 2017-12-11
|  | Testing of Ver 16.0 | Vishu, Akram | Mamta, Priyanka | 2017-01-05
|  | Time & Execution Efficiency, logging and improvement | Akram, Vishu, Aditya |  | 2017-12-10
6 | Atlas | Text Search API Improvement (OneApp) | Aditya | Testing feedback from Pradeep | 2017-12-14
|  | Atlas Improvement - Popular Index(Static) | Aditya | Data Team | 2017-12-25
|  | Atlas Improvement - Feedback API | Aditya |  | 2017-12-01
|  | Atlas Improvement - Popular Index(Dynamic) | Aditya |  | Review - 15 Dec
|  | Cleaning of Keyword on 15.1 | Aditya | Sunil | 2017-12-07
|  | Keyword improvement in 16.0 for Atlas | Aditya | Data Team (Sunil) | 2017-12-06
|  | Ingestion of Ver. 16.0 Map Data | Aditya | Sunil
|  | Ingestion of Incremental PoI Data | Aditya |  | 2017-12-11
|  | GeoCode Ver 1.0 | Aditya |  | 2017-12-30
|  | Performance Testing & Deployment | Aditya |  | 2017-12-25
7 | Traffic | Missing Segments | Ashish, Piyush | Sunil | 2017-12-10
|  | PBF on the fly generation - RnD | Ashish, Vishu, Piyush, Akram |  | 2018-01-31
Increase in Probes via Ashish Dubey(Shivalik - 8K Probes)
|  | Committed Cities for Traffic - Accuracy, Probe Assumption | Piyush, Vishu |  | 2017-12-10
|  | Ingestion of Ver. 16.0 Map Data | Ashish | Sunil (15-Dec) | 2017-12-22
|  | Scaling Up - Infra, Performance Tuning | Ashish | ARB | 2017-12-01
|  | Migration to AWS(Including Load, Performance) | Ashish | Sonal | 2017-12-22
|  | Testing (Including Consistency, Functional, data etc.) | Piyush |  | 2017-12-25
8 | InTouch | InTouch Device fetching performance issue | Ritesh |  | 2017-12-04
|  | Enhanced monitoring and queue management process | Ritesh |  | 2017-12-04
|  | InTouch API Performance Tweaking (GetEntities, GetLiveData, LocationSharing, TimeLine - Lat/ Lon Issue) | Ritesh/ Altamash |  | 2017-12-07
|  | Handling of B2B customers via a Config Flag inorder to not generate a Beacon | Ritesh |  | 2017-12-07
9 | Routing - InHouse | New Routing API - Go No Go | Piyush, Akram, Vishu |  | 2017-12-06
|  | New Routing Deployment & Testing | Piyush, Akram, Vishu |  | 2017-01-05
|  | New Routing API - Mireo |  |  | 2017-12-15
10 | Map App - Web | Web App Sprint - Gaps - UI/ UX | Abhinav |  | 2017-12-08
|  | Development | Balmukund |  | 2017-12-15
|  | Help Section | Balmukund | Anant | 2017-12-10
|  | Testing | Sonal |  | 2017-12-22
|  | Deployment | Balmukund |  | 2017-12-25
11 | Map App - Android | Integration of Explore API's | Shashank |  | 2017-12-15
|  | Integration of Traffic API's | Akram |  | 2017-12-23
|  | Integration of Text Search API | Akram |  | 2017-12-15
B2B Flag Handling
|  | Notifications Integration | Shashank |  | 2017-01-25
|  | Beta - Live Bugs Fixing | Shashank, Akram |  | Ongoing
|  | User Experience Improvements | Shashank, Akram |  | Ongoing
|  | Android Analytics, Screen By Screen & Event by Event | Shashank |  | 2017-12-07
|  | Performance Testing & Deployment Overall | Akram |  | 2017-12-07
|  | OneApp External Security Testing | Akram | Sanjay | 8th Dec, 14-Dec
ORSM Switching for Android ?
12 | Map App - iOS | Integration of Explore API's | Harshit |  | 2017-12-15
|  | Integration of Traffic API's | Harshit |  | 2017-12-23
|  | Integration of Text Search API | Harshit |  | 2017-12-15
B2B Flag Handling
|  | Level 2 Bugs | Harshit, Abhishek, Arun, Rohit |  | 2017-12-15
|  | Notifications Integration |  |  | 2017-01-25
|  | UI Cleanup UP | Rohit |  | 2017-12-28
|  | iOS Navigation | Harshit, Rohit |  | 2019-01-19
|  | iOS Analytics, Screen By Screen & Event by Event | Abhishek |  | 2017-12-28
|  | Performance Testing & Deployment Overall | Rohit |  | 2019-01-27
|  | OneApp External Security Testing |  |  | 2019-02-08
13 | Notifications | Notifications Engine | Ritesh, Anil M |  | 2017-01-15
|  | Testing Integration - iOS, Android, Web | Akram, Abhishek, Balmukund |  | 2017-01-20
14 | Data | Static ML based Priority | Ayush | Parinita (Mrs Verma) | 4-Dec (First Draft)
|  | Keywords | Aditya, Sunil |  | 2017-12-06
15 | Raster | Data handover | Mamta | Parinita, Bhupesh | 2017-12-15
|  | Data preperation | Mamta |  | 2017-01-05
|  | Tile Compilation (AWS) | Mamta |  | 2017-01-17
|  | Testing | Vishu, Akram, Monika, Aditya |  | 2017-01-20
|  | Deployment |  |  | 2017-01-21

## Workmate
S.No | Issue | Person Responsible | Dependency | Date
1 | Workmate Android App | Sahil, Deepak |  | 2017-12-15
2 | Workmate Web App | Sandeep |  | 2017-12-15
3 | Workmate iOS App | Smita |  | 2017-12-30
4 | External Security Testing | Sahil, Sandeep | Ankesh | 2017-12-25
5 | External App Testing | Sonal | Ankesh
6 | Workmate API's (Attendance, Activity) | Sandeep |  | 2017-12-15
7 | DMS | Open

## Fleet2
S.No | Team | Feature | Date | Person Responsible | Dependency
1 | InTouch | Continuos Driving | 2017-12-06 | Ajit, Ritesh
|  | Daily and Monthly Mileage Alerts |  | Ritesh, Sunil
|  | Consolidated Occurrence Report |  | Sachin, Sunil
|  | Adding Expenses |  | Sachin, Sunil
|  | Door Alarms for Cash Vans |  | Ritesh, Sachin, Sunil, Ajit
2 |  | Alarm for Servicing, Tyre Change, Insurance etc. | 2017-12-15 | Ritesh, Sachin, Sunil, Ajit
3 |  | Daily and Monthly Mileage Report | 2017-12-27 | Ritesh, Sunil
Working Hours & Non Working Hours Alarms and Reports
|  | Safety Exception Report & Alarms |  | Sachin, Sunil
|  | All Expenses Report |  | Sachin, Sunil
|  | Driver Assignement (Role) |  | Ritesh
|  | Plan Execution Report |  | Sunil